ORIGINALFORM.ORG

12-Week Launch Strategy

Product Launch Formula  ·  12 Week Year  ·  Make Time

The Deprogramming Course — From Content to Paid Launch

1. Situation & Core Insight

originalform.org is a fully built digital garden on Next.js — live, published, and already loaded with real intellectual content: essays on propaganda, power, media, debt, and institutional conditioning. A complete course called Deprogramming exists with 30+ lessons. The newsletter is wired to MailerLite via signal@originalform.org. The infrastructure is done.

The gap:  The product exists. The audience does not — yet. The next 12 weeks close that gap using Jeff Walker's Product Launch Formula as the launch engine, the 12 Week Year as the execution container, and Make Time to protect the deep work that makes it possible.

2. The Audience

Founders, intellectuals, and high-performers who sense that their thinking has been shaped by forces they have not fully examined — conditioning, media framing, institutional loyalty, social conformity. They are smart. That is the problem. They can build elegant rationalizations. The Deprogramming course gives them a framework to audit and reclaim their own cognition.

3. The Three Frameworks

Jeff Walker — Product Launch Formula (PLF)

PLF is a sequenced launch method built around psychological trust-building before asking for money. The core engine is the Sideways Sales Letter — instead of one long sales page, you deliver three pieces of free, high-value content (the Pre-Launch Sequence) over 7–10 days, then open the cart with a deadline. Each piece serves a psychological function:

PLC #1 — The Opportunity: show the transformation possible, establish the problem

PLC #2 — The Teaching: give real, actionable value; build authority and reciprocity

PLC #3 — The Experience: social proof, case studies, vision of the community; handle objections

Cart opens after PLC #3. A 5–7 email sequence runs over 5–7 days. Cart closes with a hard deadline.

The 12 Week Year

Treat 12 weeks as a complete year. Set 1–2 goals maximum. Build weekly execution plans. Score yourself each week (Did I execute my planned tasks? 85%+ = on track). Review every week. No annual planning, no drifting — just 12-week sprints with real accountability.

Goal 1: Launch the Deprogramming course and make first sales

Goal 2: Build the newsletter to 500 subscribers

Weekly scorecard: 3–5 lead measures tracked every Sunday

Make Time

Each day, pick one Highlight — the single most important task for that day related to the launch. Protect 60–90 minutes of Laser time (no phone, no social, no open tabs). Energize (sleep, move, eat). Reflect (a single sentence at night: did I do my Highlight?).

Highlight examples: write PLC email, publish newsletter issue, record course module, write sales page section

Laser tactic: phone in another room, website blockers on during Highlight block

4. The 12-Week Arc — Full Overview

| Phase | Weeks | Primary Goal |
| --- | --- | --- |
| SEED | Weeks 1–3 | Launch the newsletter. Build the list. Publish cornerstone content. |
| WARM | Weeks 4–6 | Pre-Launch Content Sequence (PLF). Open the waitlist. |
| LAUNCH | Weeks 7–8 | Cart open. Email sequence. First sales of Deprogramming course. |
| DELIVER | Weeks 9–12 | Onboard buyers. Deliver course. Gather feedback. Plan next cycle. |

5. Week-by-Week Execution Plan

| Week | 12WY Goal / PLF Stage | Key Actions | Make Time Highlight |
| --- | --- | --- | --- |

| Week 1 | SEED — Foundation | Set up MailerLite welcome sequence (3 emails). Write and schedule newsletter issue #1. Define course price point ($97–$197). Set up simple landing page for waitlist. | Write welcome email sequence |
| --- | --- | --- | --- |

| Week 2 | SEED — Audience | Publish newsletter issue #2. Post "Why Propaganda Works on Smart People" to social (repurpose from existing post). Add email capture CTA to every blog post. Set up basic analytics. | Write + send newsletter #2 |
| --- | --- | --- | --- |

| Week 3 | SEED — Warm-Up | Newsletter issue #3 (teach one concept from the course). Begin seeding "something is coming" language in emails. DM or email 10 people personally who would resonate. | Seed the teaser in newsletter #3 |
| --- | --- | --- | --- |

| Week 4 | WARM — PLC #1 | Pre-Launch Content #1: The Opportunity. Write and send a long-form email or post: "What Deprogramming Actually Is — and Why Smart People Need It Most." Announce waitlist is open. | Write and publish PLC #1 |
| --- | --- | --- | --- |

| Week 5 | WARM — PLC #2 | Pre-Launch Content #2: The Teaching. Give away a real lesson — use the "What is Deprogramming?" module. Show the framework. Make it immediately useful. Link to waitlist. | Produce and send PLC #2 teaching piece |
| --- | --- | --- | --- |

| Week 6 | WARM — PLC #3 | Pre-Launch Content #3: The Experience + Objections. Share social proof (even early readers). Address "Is this for me?" "Do I have time?" "Will this actually work?" Close with: "Doors open Monday." | Write PLC #3 and handle objections clearly |
| --- | --- | --- | --- |

| Week 7 | LAUNCH — Cart Open | Monday: Cart opens. Send Launch Email #1 (the offer). Publish full sales page. Tuesday: Email #2 (testimonial / FAQ). Thursday: Email #3 (teaching + soft push). Friday: Email #4 (deadline reminder). | Send launch email #1 on Monday morning |
| --- | --- | --- | --- |

| Week 8 | LAUNCH — Close | Monday: Email #5 (why this matters, last call). Tuesday midnight: Cart closes. Send "closed" email. Onboard all buyers immediately. Send welcome + access details. | Write and send cart-close email |
| --- | --- | --- | --- |

| Week 9 | DELIVER — Onboarding | Welcome buyers with a kickoff email. Set up course access page (already in codebase at /course-access). Send first lesson. Begin gathering feedback after lesson 1. | Onboard buyers and send first lesson |
| --- | --- | --- | --- |

| Week 10 | DELIVER — Momentum | Continue delivering course content weekly. Send one newsletter issue to the broader list (non-buyers). Begin collecting testimonials from early students. | Collect 3 testimonials from buyers |
| --- | --- | --- | --- |

| Week 11 | DELIVER — Refinement | Survey buyers mid-course. Adjust any unclear lessons. Write a post-launch debrief for yourself. Identify what resonated most in PLF sequence. | Run mid-course survey + note insights |
| --- | --- | --- | --- |

| Week 12 | DELIVER — Next Cycle | Final delivery. Plan next 12-week cycle (next launch, next product, higher price, or cohort format). Newsletter issue announcing what's next. Celebrate the launch. | Plan 12WY cycle #2 — write the next vision |
| --- | --- | --- | --- |

6. Newsletter Strategy

The newsletter is the primary trust-building channel. Every issue should do one of three things: teach a thinking framework, challenge a dominant narrative, or show readers something they cannot unsee. Each issue seeds the eventual launch naturally — readers who trust the free content buy the paid course.

Content Pillars

Propaganda & Media — How narratives are manufactured and how to detect them

Power & Institutions — How systems shape behavior without using force

Cognitive Sovereignty — Practical tools for clearer, independent thinking

The Deprogramming Framework — Direct lessons from the course, released free

Cadence

Weeks 1–3: Weekly (build the habit, seed the list)

Weeks 4–6: Weekly + PLF emails (separate from newsletter — use MailerLite segments)

Weeks 7–8: Launch emails only — pause regular newsletter during cart open

Weeks 9–12: Resume weekly newsletter; include course insights for non-buyers

Tip:  Use the EMAIL_GROUP_MAP config already in the codebase to separate newsletter subscribers from course waitlist signups. This lets you send PLF emails only to warm leads, not your entire list.

7. Launch Week Email Sequence (7 Emails)

Email 1 — Monday  (The Offer)

Subject: Deprogramming is open.

Body: Short, direct. "The course is live. Here is what it is, who it is for, and what it costs. [Link]." No fluff. Confident tone — this is for people who already trust you.

Email 2 — Tuesday  (The Teaching Email)

Subject: One thing the course teaches that most people never learn

Body: Give away a key insight from the course — e.g., how institutions manage attention. End with a soft CTA: "The full course goes deeper. [Link]."

Email 3 — Wednesday  (The FAQ / Objections)

Subject: "Is this course for me?" — answered honestly

Body: Address the 3 main objections: time, skepticism, price. Be real. "If you're already reading this newsletter, it's probably for you."

Email 4 — Thursday  (Social Proof)

Subject: What early readers said

Body: 2–3 quotes from people who've read the content or taken early access. Keep it human and specific — not marketing language.

Email 5 — Friday  (The Reminder)

Subject: Closing Sunday

Body: Two sentences. "Cart closes Sunday midnight. If it's been on your mind, this is the nudge." [Link]

Email 6 — Sunday AM  (Last Day)

Subject: Today is the last day

Body: Remind them of the transformation. Paint the before/after. Restate the deadline clearly.

Email 7 — Sunday PM  (Final Hours)

Subject: Closes at midnight

Body: Ultra short. "Last call. [Link]. After midnight, the course closes." Nothing more.

8. Weekly Scorecard Template

Review every Sunday. Score your lead measures for the week — not outcomes, but executions. 85%+ means you are on track. Below 85%, identify one blocker and remove it before Monday.

| Lead Measure | Target | Actual | Score |
| --- | --- | --- | --- |
| Newsletter issue sent | 1 / week | ___ | ___ |
| Make Time Highlight done | 5 / week | ___ | ___ |
| New email subscribers | 25 / week | ___ | ___ |
| PLF / launch email written | per plan | ___ | ___ |
| Deep work blocks (60+ min) | 4 / week | ___ | ___ |
| Social post / content piece | 2 / week | ___ | ___ |
| Weekly review completed | 1 / week | ___ | ___ |

Scoring formula:  Tasks completed ÷ Tasks planned × 100 = Execution score. Target 85%+. If you hit 85%+ for 8 of 12 weeks, you will launch.

9. Product Format — Decision Guide

The Deprogramming course content exists as 30+ MDX lessons. The format choice affects price, delivery, and conversion. Recommendation for a first launch:

| Format | Price Range | Effort to Launch | Recommended? |
| --- | --- | --- | --- |
| Self-paced course (MDX) | $97–$197 | Low — already built | ✓ Start here |
| Cohort / live course | $297–$997 | High — scheduling, live calls | Cycle 2+ |
| PDF / Ebook | $17–$47 | Very low | Complementary upsell |

Recommendation:  Launch the self-paced course first at $127. The /course-access route is already in the codebase. Use MailerLite to deliver access via email after purchase (or integrate Gumroad/Lemon Squeezy for payments). Move to a live cohort in cycle 2 once you have testimonials and proof of concept.

10. Technical Checklist (Before Launch)

☐  Set NEXT_PUBLIC_BASE_URL to https://originalform.org in Vercel env vars

☐  Set EMAIL_API_KEY and EMAIL_LIST_UUIDS for MailerLite in Vercel env vars

☐  Set EMAIL_GROUP_MAP with groups: newsletter:<id>, deprogramming:<id>

☐  Create a Waitlist group in MailerLite and wire to the course landing page form

☐  Build a simple /deprogramming sales page (use existing Hero + MDX layout)

☐  Wire /course-access to validate email and grant course access

☐  Set up Gumroad or Lemon Squeezy for payment processing (connect to MailerLite on purchase)

☐  Add email capture CTA to bottom of every published post (not just homepage)

☐  Test the full subscriber → welcome email → course access flow end-to-end

☐  Set up Plausible or Umami analytics to track signups, page views, and conversions

The Single Most Important Thing

The product is built. The content is real. The audience is the work now.
Send the newsletter. Write the emails. Ship the launch.
Everything else is resistance dressed up as planning.

originalform.org  ·  signal@originalform.org  ·  12-Week Launch Cycle